## Legend & Setup
Project Start Date (edit this cell) | 2026-07-20
Role color legend
Phase 0 - Proposal & Planning
Phase 1 - System Design
Phase 2 - Single Door-Node Prototype
Phase 3 - Backend & Database
Phase 4 - Dashboard
Phase 5 - Security & Fail-Safe
Phase 6 - Multi-Node Scaling
Phase 7 - Full System Testing
Phase 8 - Documentation
Phase 9 - Presentation & Defense Prep
Roles
Whole Team (PM)
Embedded/Firmware
Hardware/Circuit
Backend/Database
Frontend/Dashboard
Network/Security
QA/Documentation

## Project Timeline
Phase | ID | Task | Owner | Start Wk | End Wk | Duration (wk) | Start Date | End Date | Dependencies | Status | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34
Phase 0 - Proposal & Planning | P0.1 | Finalize architecture decisions (credential type, network topology, fail-safe/fail-secure) | Whole Team (PM) | 1 | 1 | 1 | 2026-07-20 | 2026-07-26 |  | Not Started
Phase 0 - Proposal & Planning | P0.2 | Research related/competitor systems (Genetec, Salto, HID) | Network/Security | 1 | 2 | 2 | 2026-07-20 | 2026-08-02 |  | Not Started
Phase 0 - Proposal & Planning | P0.3 | Revise proposal document (architecture, stack, security, risk, budget) | Whole Team (PM) | 1 | 2 | 2 | 2026-07-20 | 2026-08-02 | P0.1 | Not Started
Phase 0 - Proposal & Planning | P0.4 | Draft budget & bill of materials (BOM) | Hardware/Circuit | 2 | 2 | 1 | 2026-07-27 | 2026-08-02 | P0.1 | Not Started
Phase 0 - Proposal & Planning | P0.5 | Draft risk & mitigation section | Whole Team (PM) | 2 | 2 | 1 | 2026-07-27 | 2026-08-02 |  | Not Started
Phase 0 - Proposal & Planning | P0.6 | Assign roles & build project timeline | Whole Team (PM) | 1 | 1 | 1 | 2026-07-20 | 2026-07-26 |  | Not Started
Phase 0 - Proposal & Planning | P0.7 | Supervisor review & proposal sign-off | Whole Team (PM) | 3 | 3 | 1 | 2026-08-03 | 2026-08-09 | P0.3 | Not Started
Phase 0 - Proposal & Planning | P0.8 | Order hardware components | Hardware/Circuit | 3 | 3 | 1 | 2026-08-03 | 2026-08-09 | P0.4,P0.7 | Not Started
Phase 1 - System Design | P1.1 | Draw system block diagram (3-layer architecture) | Network/Security | 3 | 4 | 2 | 2026-08-03 | 2026-08-16 | P0.7 | Not Started
Phase 1 - System Design | P1.2 | Design door-node circuit schematic | Hardware/Circuit | 3 | 5 | 3 | 2026-08-03 | 2026-08-23 | P0.7 | Not Started
Phase 1 - System Design | P1.3 | Simulate circuit in Proteus/Multisim before build | Hardware/Circuit | 5 | 5 | 1 | 2026-08-17 | 2026-08-23 | P1.2 | Not Started
Phase 1 - System Design | P1.4 | Define DB schema (users, credentials, doors, schedules, logs) | Backend/Database | 4 | 5 | 2 | 2026-08-10 | 2026-08-23 | P1.1 | Not Started
Phase 1 - System Design | P1.5 | Define REST API spec | Backend/Database | 5 | 5 | 1 | 2026-08-17 | 2026-08-23 | P1.4 | Not Started
Phase 1 - System Design | P1.6 | Define MQTT topics / RS-485 message format | Network/Security | 5 | 5 | 1 | 2026-08-17 | 2026-08-23 | P1.1 | Not Started
Phase 1 - System Design | P1.7 | Define firmware state machine for door node | Embedded/Firmware | 4 | 5 | 2 | 2026-08-10 | 2026-08-23 | P1.1 | Not Started
Phase 1 - System Design | P1.8 | Write security design doc (encryption, credential storage, tamper detection) | Network/Security | 5 | 6 | 2 | 2026-08-17 | 2026-08-30 | P1.6 | Not Started
Phase 1 - System Design | P1.9 | Design dashboard wireframes/UI mockups | Frontend/Dashboard | 5 | 6 | 2 | 2026-08-17 | 2026-08-30 | P1.4 | Not Started
Phase 1 - System Design | P1.10 | Design review with supervisor | Whole Team (PM) | 6 | 6 | 1 | 2026-08-24 | 2026-08-30 | P1.1,P1.2,P1.4,P1.7,P1.8,P1.9 | Not Started
Phase 2 - Single Door-Node Prototype | P2.1 | Assemble breadboard: card/biometric reader + MCU | Embedded/Firmware | 6 | 7 | 2 | 2026-08-24 | 2026-09-06 | P1.10,P0.8 | Not Started
Phase 2 - Single Door-Node Prototype | P2.2 | Wire relay/lock actuator driver circuit | Hardware/Circuit | 7 | 7 | 1 | 2026-08-31 | 2026-09-06 | P1.3,P0.8 | Not Started
Phase 2 - Single Door-Node Prototype | P2.3 | Wire door-state sensor (reed switch/Hall sensor) | Hardware/Circuit | 7 | 7 | 1 | 2026-08-31 | 2026-09-06 | P0.8 | Not Started
Phase 2 - Single Door-Node Prototype | P2.4 | Firmware: credential reader input handling | Embedded/Firmware | 7 | 8 | 2 | 2026-08-31 | 2026-09-13 | P2.1 | Not Started
Phase 2 - Single Door-Node Prototype | P2.5 | Firmware: lock actuation logic | Embedded/Firmware | 8 | 8 | 1 | 2026-09-07 | 2026-09-13 | P2.2,P2.4 | Not Started
Phase 2 - Single Door-Node Prototype | P2.6 | Firmware: door-state polling & debounce | Embedded/Firmware | 8 | 9 | 2 | 2026-09-07 | 2026-09-20 | P2.3,P2.4 | Not Started
Phase 2 - Single Door-Node Prototype | P2.7 | Implement network client on node (Wi-Fi/MQTT or RS-485 driver) | Embedded/Firmware | 9 | 10 | 2 | 2026-09-14 | 2026-09-27 | P1.6,P2.4 | Not Started
Phase 2 - Single Door-Node Prototype | P2.8 | Bench test lock actuation & timing accuracy | Hardware/Circuit | 10 | 10 | 1 | 2026-09-21 | 2026-09-27 | P2.5 | Not Started
Phase 2 - Single Door-Node Prototype | P2.9 | Validate power supply & isolation circuit | Hardware/Circuit | 10 | 10 | 1 | 2026-09-21 | 2026-09-27 | P2.2 | Not Started
Phase 2 - Single Door-Node Prototype | P2.10 | Integration test: single door node end-to-end | Whole Team (PM) | 11 | 11 | 1 | 2026-09-28 | 2026-10-04 | P2.6,P2.7,P2.8,P2.9 | Not Started
Phase 3 - Backend & Database | P3.1 | Set up repo, dev environment, CI basics | Backend/Database | 8 | 8 | 1 | 2026-09-07 | 2026-09-13 | P1.5 | Not Started
Phase 3 - Backend & Database | P3.2 | Implement DB schema in chosen engine | Backend/Database | 8 | 9 | 2 | 2026-09-07 | 2026-09-20 | P3.1,P1.4 | Not Started
Phase 3 - Backend & Database | P3.3 | Build authentication/authorization module | Backend/Database | 9 | 10 | 2 | 2026-09-14 | 2026-09-27 | P3.2 | Not Started
Phase 3 - Backend & Database | P3.4 | Build credential management (issue/revoke) | Backend/Database | 10 | 10 | 1 | 2026-09-21 | 2026-09-27 | P3.3 | Not Started
Phase 3 - Backend & Database | P3.5 | Build scheduling engine w/ mock registrar timetable import | Backend/Database | 11 | 12 | 2 | 2026-09-28 | 2026-10-11 | P3.2 | Not Started
Phase 3 - Backend & Database | P3.6 | Build MQTT/HTTP listener for door-node events | Backend/Database | 12 | 12 | 1 | 2026-10-05 | 2026-10-11 | P2.7,P3.1 | Not Started
Phase 3 - Backend & Database | P3.7 | Build audit-log service | Backend/Database | 12 | 13 | 2 | 2026-10-05 | 2026-10-18 | P3.6 | Not Started
Phase 3 - Backend & Database | P3.8 | Unit test backend endpoints | Backend/Database | 13 | 14 | 2 | 2026-10-12 | 2026-10-25 | P3.3,P3.5,P3.6,P3.7 | Not Started
Phase 4 - Dashboard | P4.1 | Scaffold frontend project | Frontend/Dashboard | 11 | 11 | 1 | 2026-09-28 | 2026-10-04 | P1.9 | Not Started
Phase 4 - Dashboard | P4.2 | Build login/auth UI | Frontend/Dashboard | 11 | 12 | 2 | 2026-09-28 | 2026-10-11 | P4.1,P3.3 | Not Started
Phase 4 - Dashboard | P4.3 | Build real-time door-status view | Frontend/Dashboard | 13 | 14 | 2 | 2026-10-12 | 2026-10-25 | P4.2,P3.6 | Not Started
Phase 4 - Dashboard | P4.4 | Build manual override controls | Frontend/Dashboard | 14 | 14 | 1 | 2026-10-19 | 2026-10-25 | P4.3 | Not Started
Phase 4 - Dashboard | P4.5 | Build historical logs & charts view | Frontend/Dashboard | 15 | 15 | 1 | 2026-10-26 | 2026-11-01 | P3.7 | Not Started
Phase 4 - Dashboard | P4.6 | Build alerts/notifications UI | Frontend/Dashboard | 15 | 16 | 2 | 2026-10-26 | 2026-11-08 | P4.3 | Not Started
Phase 4 - Dashboard | P4.7 | Integrate dashboard with backend API (full pipeline) | Frontend/Dashboard | 16 | 17 | 2 | 2026-11-02 | 2026-11-15 | P4.4,P4.5,P4.6,P3.8 | Not Started
Phase 5 - Security & Fail-Safe | P5.1 | Implement credential encryption in transit & at rest | Network/Security | 15 | 15 | 1 | 2026-10-26 | 2026-11-01 | P1.8,P3.4 | Not Started
Phase 5 - Security & Fail-Safe | P5.2 | Implement tamper-detection logic | Network/Security | 16 | 16 | 1 | 2026-11-02 | 2026-11-08 | P2.6,P5.1 | Not Started
Phase 5 - Security & Fail-Safe | P5.3 | Implement fail-safe/fail-secure power-loss behavior | Hardware/Circuit | 16 | 17 | 2 | 2026-11-02 | 2026-11-15 | P2.9,P0.1 | Not Started
Phase 5 - Security & Fail-Safe | P5.4 | Implement local fallback on network loss | Embedded/Firmware | 17 | 18 | 2 | 2026-11-09 | 2026-11-22 | P2.7,P5.3 | Not Started
Phase 5 - Security & Fail-Safe | P5.5 | Internal security review / basic penetration test | Network/Security | 18 | 19 | 2 | 2026-11-16 | 2026-11-29 | P5.1,P5.2,P5.4 | Not Started
Phase 6 - Multi-Node Scaling | P6.1 | Fabricate/assemble 3-4 additional door nodes | Hardware/Circuit | 18 | 20 | 3 | 2026-11-16 | 2026-12-06 | P2.10 | Not Started
Phase 6 - Multi-Node Scaling | P6.2 | Deploy nodes on shared network/backbone | Network/Security | 20 | 21 | 2 | 2026-11-30 | 2026-12-13 | P6.1 | Not Started
Phase 6 - Multi-Node Scaling | P6.3 | Load-test backend with concurrent nodes | Backend/Database | 21 | 21 | 1 | 2026-12-07 | 2026-12-13 | P6.2,P3.8 | Not Started
Phase 6 - Multi-Node Scaling | P6.4 | Fix integration/scaling bugs | Whole Team (PM) | 22 | 23 | 2 | 2026-12-14 | 2026-12-27 | P6.3 | Not Started
Phase 7 - Full System Testing | P7.1 | Execute functional test plan (scheduled/override/logging modes) | QA/Documentation | 23 | 24 | 2 | 2026-12-21 | 2027-01-03 | P6.4,P4.7 | Not Started
Phase 7 - Full System Testing | P7.2 | Fail-safe validation test (simulate power/network loss) | Hardware/Circuit | 24 | 24 | 1 | 2026-12-28 | 2027-01-03 | P5.3,P5.4 | Not Started
Phase 7 - Full System Testing | P7.3 | Security test (cloning attempt, encryption verification) | Network/Security | 25 | 25 | 1 | 2027-01-04 | 2027-01-10 | P5.5 | Not Started
Phase 7 - Full System Testing | P7.4 | Dashboard load/performance test | Frontend/Dashboard | 25 | 25 | 1 | 2027-01-04 | 2027-01-10 | P4.7 | Not Started
Phase 7 - Full System Testing | P7.5 | Bug fixing & regression testing | Whole Team (PM) | 26 | 27 | 2 | 2027-01-11 | 2027-01-24 | P7.1,P7.2,P7.3,P7.4 | Not Started
Phase 8 - Documentation | P8.1 | Draft report: Introduction & Problem Statement | Whole Team (PM) | 26 | 26 | 1 | 2027-01-11 | 2027-01-17 |  | Not Started
Phase 8 - Documentation | P8.2 | Draft report: System Architecture & Design | Embedded/Firmware | 27 | 27 | 1 | 2027-01-18 | 2027-01-24 | P1.10 | Not Started
Phase 8 - Documentation | P8.3 | Draft report: Implementation chapters | Backend/Database | 28 | 28 | 1 | 2027-01-25 | 2027-01-31 | P7.5 | Not Started
Phase 8 - Documentation | P8.4 | Draft report: Testing & Evaluation results | QA/Documentation | 29 | 29 | 1 | 2027-02-01 | 2027-02-07 | P7.5 | Not Started
Phase 8 - Documentation | P8.5 | Write user/deployment manual | Whole Team (PM) | 29 | 30 | 2 | 2027-02-01 | 2027-02-14 | P7.5 | Not Started
Phase 8 - Documentation | P8.6 | Full report review & editing | Whole Team (PM) | 30 | 31 | 2 | 2027-02-08 | 2027-02-21 | P8.1,P8.2,P8.3,P8.4,P8.5 | Not Started
Phase 8 - Documentation | P8.7 | Submit final report | Whole Team (PM) | 31 | 31 | 1 | 2027-02-15 | 2027-02-21 | P8.6 | Not Started
Phase 9 - Presentation & Defense Prep | P9.1 | Build presentation slides | Whole Team (PM) | 31 | 32 | 2 | 2027-02-15 | 2027-02-28 | P8.6 | Not Started
Phase 9 - Presentation & Defense Prep | P9.2 | Prepare live demo script & backup plan | Whole Team (PM) | 32 | 32 | 1 | 2027-02-22 | 2027-02-28 | P7.5 | Not Started
Phase 9 - Presentation & Defense Prep | P9.3 | Rehearse defense Q&A | Whole Team (PM) | 33 | 33 | 1 | 2027-03-01 | 2027-03-07 | P9.1,P9.2 | Not Started
Phase 9 - Presentation & Defense Prep | P9.4 | Final equipment check & demo dry run | Whole Team (PM) | 33 | 34 | 2 | 2027-03-01 | 2027-03-14 | P9.2 | Not Started
Phase 9 - Presentation & Defense Prep | P9.5 | Project defense | Whole Team (PM) | 34 | 34 | 1 | 2027-03-08 | 2027-03-14 | P9.3,P9.4 | Not Started